## project-roadmap
Project Roadmap
Company Set Up
Name | Subitems | Person | Status | Timeline - Start | Timeline - End
QA Manual Draft | Documentation Section, Project Management Section, Software Manager Role, Design & Marketing Manager Role, QA Manager Role, Communications Manager Role, Documentation Manager Role, Finance Manager Role, Version Control Manager Role, Agile Development Section | Leadership, Documentation, Marketing, Development, QA, Finance | Done | 2022-11-18 | 2022-11-25
Subitems | Name | Person | Status | Start Date | Finish Date
| Documentation Section | Jonathan Cooke | Done | 2022-11-25
| Project Management Section | Sidharth Shanmugam | Done | 2022-11-25
| Software Manager Role | Fraser Todd | Done | 2022-11-25
| Design & Marketing Manager Role | Sophie | Done | 2022-11-25
| QA Manager Role | Paul Pickering | Done | 2022-11-25
| Communications Manager Role | Oli Partidge | Done | 2022-11-25
| Documentation Manager Role | Jonathan Cooke | Done | 2022-11-25
| Finance Manager Role | Srikanth Jakka | Done | 2022-11-25
| Version Control Manager Role | Srikanth Jakka | Done | 2022-11-25
| Agile Development Section |  | Done
Generate Project Ideas |  |  | Done | 2022-10-16 | 2022-10-30
Generate Team Roles |  |  | Done | 2022-10-17 | 2022-10-30
Clear Initial Project Queries |  |  | Done | 2022-10-30 | 2022-11-04
Finalise Team Roles |  |  | Done | 2022-11-06 | 2022-11-06
Finalise Project Idea |  |  | Done | 2022-11-06 | 2022-11-06
Submit Functional Specification Draft 1 |  |  | Done | 2022-11-18 | 2022-11-18
Submit QA Manual Draft |  |  | Done | 2022-12-02 | 2022-12-02
Finance Overview |  | Srikanth Jakka | Done | 2022-11-04 | 2022-11-07
Functional Specification Overview |  | Leadership | Done | 2022-11-04 | 2022-11-09
Write Functional Specification Draft 1 |  | Leadership | Done | 2022-11-09 | 2022-11-17
QA Manual Overview |  | Leadership | Done | 2022-11-04 | 2022-11-09
Write QA Manual Draft 1 |  | Leadership | Done | 2022-11-09 | 2022-11-17
Customer Profile |  |  | Done | 2022-11-14 | 2022-11-18
User Profile |  | Sarujan Thevathasan | Done | 2022-11-14 | 2022-11-22
Design: Descriptions |  | Sophie | Done | 2022-11-22 | 2022-11-29
Design: Mock-ups |  | Sarujan Thevathasan | Done | 2022-11-22 | 2022-11-28
User Survey |  | Oli Partidge | Done | 2022-11-14 | 2022-11-29
Marketing and Design | Company and App Name, Mock up 2, Layout mockups (for final integration), Colour Scheme, In- app Icons: curation, App Icon: Final, App Logo (to be used in app): Rough, App Logo: Final, App Icon (not in-app): Draft, Map design: XML, Map Design: Final, 1st iteration of surveys: Distributing, 1st Itteration of surveys: Collecting and Analysing, Beta Testing: Collecting and Analysing, Last Presentation: drafting presentation, Last Presentation: creation of visual aditions, Last presentation: creation of charts to show survey statistics, Company Logo: Final, Beta Testing: creating review form, Beta Testing: Organising beta testing, Last presentation: Organise group mock presentation, HTML mock ups |  | Done | 2023-02-14 | 2023-02-17
Subitems | Name | Person | Status | Start Date | Finish Date
| Company and App Name | Oli Partidge | Done | 2023-01-16
| Mock up 2 | Sarujan Thevathasan | Done | 2023-01-16
| Company Logo: Final | Sophie | Done | 2023-02-20 | 2023-02-27
| Colour Scheme | Sophie | Done | 2023-02-27 | 2023-03-06
| In- app Icons: curation | Sarujan Thevathasan | Done | 2023-02-20 | 2023-02-27
| App Icon (not in-app): Draft | Sarujan Thevathasan | Done | 2023-02-20 | 2023-02-27
| App Icon: Final | Sarujan Thevathasan | Done | 2023-02-27 | 2023-03-06
| App Logo (to be used in app): Rough | Sarujan Thevathasan | Done | 2023-02-14
| App Logo: Final | Sarujan Thevathasan | Done | 2023-02-15 | 2023-02-20
| Map design: XML | Sarujan Thevathasan | Done | 2023-04-21 | 2023-04-28
| Map Design: Final |  | Done | 2023-03-06 | 2023-03-13
| 1st iteration of surveys: Distributing | Sophie | Done | 2023-03-06 | 2023-03-16
| 1st Itteration of surveys: Collecting and Analysing | jwh535@york.ac.uk | Done | 2023-04-21 | 2023-04-28
| Layout mockups (for final integration) | Sophie | Done | 2023-04-17 | 2023-04-24
| HTML mock ups |  | Done | 2023-05-07
| Beta Testing: creating review form |  | Done | 2023-05-08 | 2023-05-15
| Beta Testing: Organising beta testing | Matteo Pearce | Done | 2023-04-21 | 2023-04-28
| Beta Testing: Collecting and Analysing |  | Done | 2023-05-15 | 2023-05-22
| Last Presentation: drafting presentation |  | Done | 2023-05-22 | 2023-05-29
| Last Presentation: creation of visual aditions |  | Done | 2023-05-22 | 2023-05-29
| Last presentation: creation of charts to show survey statistics |  | Done | 2023-05-22 | 2023-05-29
| Last presentation: Organise group mock presentation |  | Done | 2023-05-29 | 2023-06-05
|  |  |  | 2022-10-16 | 2023-02-17