## project-roadmap
Project Roadmap
Project Specification & First Iteration
Name | Subitems | Person | Status | Timeline - Start | Timeline - End
Submit Functional Specification Draft 2 |  | Leadership | Done | 2023-01-20 | 2023-01-20
Submit Final Functional Specification | Improve Project Overview statement |  | Done | 2023-02-03 | 2023-02-03
Subitems | Name | Person | Status | Start Date | Finish Date
| Improve Project Overview statement | Jonathan Cooke, Sophie | Done
Submit Final QA Manual | Add actions if risks occur to Risk Management Tables, Add clear measurements for QA metrics, Improve Test Engineer Section 2.3.2 with what is good or bad, Clearly delineate Finance Manager and Accountant roles, Remove timesheets from Project Manager role |  | Done | 2023-02-06 | 2023-02-06
Subitems | Name | Person | Status | Start Date | Finish Date
| Add actions if risks occur to Risk Management Tables | Jonathan Cooke, Sidharth Shanmugam, Luke George, jwh535@york.ac.uk, Srikanth Jakka, Sophie, Oli Partidge, Paul Pickering, Sarujan Thevathasan, Fraser Todd, Matteo Pearce | Done
| Add clear measurements for QA metrics | Jonathan Cooke, Sidharth Shanmugam, Luke George, jwh535@york.ac.uk, Srikanth Jakka, Sophie, Oli Partidge, Sarujan Thevathasan, Paul Pickering, Fraser Todd, Matteo Pearce | Done
| Improve Test Engineer Section 2.3.2 with what is good or bad | QA | Done
| Clearly delineate Finance Manager and Accountant roles | Finance | Done
| Remove timesheets from Project Manager role | Jonathan Cooke | Done
Submit Financial Business Plan |  |  | Done | 2023-02-10 | 2023-02-10
Intergroup Contracts Exchange | Negotiations catch-up, Financial terms write up, Create general contract structure, Software terms write-up, Initial Exchange, Intergroup initial exchange catch-up |  | Done | 2023-02-13 | 2023-02-13
Subitems | Name | Person | Status | Start Date | Finish Date
| Create general contract structure | Sidharth Shanmugam | Done | 2023-02-09
| Negotiations catch-up | Sidharth Shanmugam, Oli Partidge, Matteo Pearce | Done | 2023-02-07 16:00
| Financial terms write up | Luke George, Srikanth Jakka | Done | 2023-02-09
| Software terms write-up | Fraser Todd | Done | 2023-02-09
| Initial Exchange |  | Done | 2023-02-13
| Intergroup initial exchange catch-up |  | Done | 2023-02-15
Project Wide Standards Agreement |  |  | Done | 2023-02-16 | 2023-02-16
Group Tender Presentation | Obtain Ethics Approval For Surveys, Arrange Talks with YUSU |  | Done | 2023-02-20 | 2023-02-20
Subitems | Name | Person | Status | Start Date | Finish Date
Obtain Ethics Approval For Surveys
Arrange Talks with YUSU
Submit Financial Report 1 |  |  | Done | 2023-02-24 | 2023-02-24
All Contracts Agreed and Filed |  |  | Done | 2023-02-28 | 2023-02-28
Submit Financial Report 2 |  |  | Done | 2023-03-10 | 2023-03-10
First Iteration Completion |  |  | Done | 2023-03-17 | 2023-03-17
Submit Final Test & Integration Plan |  |  | Done | 2023-03-17 | 2023-03-17
|  |  |  | 2023-01-20 | 2023-03-17