## project-roadmap
Project Roadmap
Second Iteration & Delivery
Name | Subitems | Person | Status | Timeline - Start | Timeline - End
HTML Tour | List all of the documentation that needs to be in the tour, Make a tree/hierarchy diagram of all the webpages in the tour, Create designs for each web page, Construct HTML Tour |  | Working on it | 2023-06-08 | 2023-06-08
Subitems | Name | Person | Status | Start Date | Finish Date
| List all of the documentation that needs to be in the tour | Srikanth Jakka, Jonathan Cooke | Done |  | 2023-03-17
| Make a tree/hierarchy diagram of all the webpages in the tour | Jonathan Cooke, Srikanth Jakka | Done |  | 2023-03-17
| Create designs for each web page | Sidharth Shanmugam, Oli Partidge | Done |  | 2023-05-07
| Construct HTML Tour | Sidharth Shanmugam | Working on it |  | 2023-05-14
Submit Financial Report 3 |  |  | Done | 2023-05-05 | 2023-05-05
Submit Financial Summary Report |  |  | Done | 2023-05-26 | 2023-05-26
Demonstration & Sales Presentation |  |  | Done | 2023-06-05 | 2023-06-05
User Manual |  | Jonathan Cooke, Sidharth Shanmugam | Done | 2023-06-08 | 2023-06-08
Submit All Deliverables |  |  | Working on it | 2023-06-08 | 2023-06-08
|  |  |  | 2023-05-05 | 2023-06-08