## Sheet1
Week
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
|  | Task timeline |  | Draft FS |  | Functional Spec | QA Manual | PWS Agreed | Group Tender Presentations | Contracts | Financial Report II | First Iteration |  |  |  |  | Financial Report III | Financial Summary |  |  |  | All Deliverables
[7 empty] | Financial Business Plan |  | Financial Report I
QA Manual
|  |  | Week 8: 10.42 | [10 empty] | QA Audits
[7 empty] | 40 | 4 | 1 | 20 | 10 | 10 | 2 | 4 | 5 | 5 | 0.5/week | 1 | 60 |  |  |  | PWS
| Deadline | Total Hours | Projected Hours | Term Week | Date (Week End Fri) | Plan Week | QA Manual | QA Audits | PWS | Functional Specification | Design Documentation | User Manual | Inter-group Contracts | Test and Integration plans and reports | Financial Report | Source Code | Minutes of Meetings | Multimedia Presentation | HTML Tour | Manager Role |  |  | Functional Specification
|  |  | Week 2: 2; Week 3: 2022-10-07; Week 4: 2 |  |  |  |  | 0.25 | [5 empty] | Design Documentation
|  |  | Week 2: 3; Week 3: 2022-10-14; Week 4: 3 |  |  |  |  | 0.25 | [5 empty] | User Manual
|  |  | Week 2: 4; Week 3: 2022-10-21; Week 4: 4 |  |  |  |  | 0.25 | [5 empty] | Inter-group Contracts
|  |  | Week 2: 5; Week 3: 2022-10-28; Week 4: 5 |  |  |  |  | 0.25 | [5 empty] | Test and Integration plans and reports
|  |  | Week 2: 6; Week 3: 2022-11-04; Week 4: 6 |  |  |  |  | 0.25 | [5 empty] | Financial Report
|  |  | Week 2: 7; Week 3: 2022-11-11; Week 4: 7; Week 8: 0.5 |  |  |  |  | 0.25 | [5 empty] | Source Code
|  |  | Week 2: 8; Week 3: 2022-11-18; Week 4: 8; Week 8: 1.75 |  |  |  |  | 0.25 | [5 empty] | Minutes of Meetings
|  |  | Week 2: 9; Week 3: 2022-11-25; Week 4: 9; Week 5: 2 |  |  |  |  | 0.25 | [5 empty] | Multimedia Presentation
|  |  | Week 2: 10; Week 3: 2022-12-02; Week 4: 10 |  |  |  |  | 0.25 | [5 empty] | HTML Tour
|  |  | Week 3: 2022-12-09; Week 4: 11 |  |  |  |  | 0.25
|  |  | Week 3: 2022-12-16; Week 4: 12 |  |  |  |  | 0.25
|  |  | Week 3: 2022-12-23; Week 4: 13 |  |  |  |  | 0.25
|  |  | Week 3: 2022-12-30; Week 4: 14 |  |  |  |  | 0.25
|  |  | Week 3: 2023-01-06; Week 4: 15 |  |  |  |  | 0.25
|  |  | Week 2: 1; Week 3: 2023-01-13; Week 4: 16 |  |  |  |  | 0.25
| Draft FS | 10 | Week 2: 2; Week 3: 2023-01-20; Week 4: 17; Week 8: 4.17; Week 9: 2 |  |  |  |  | 0.25
|  |  | Week 2: 3; Week 3: 2023-01-27; Week 4: 18; Week 9: 2 |  |  |  |  | 0.25
| Functional Spec | 10 |  | 4 | 2023-02-03 | 19 | 2 |  |  | 4 | 2 | [5 empty] | 0.25
Financial Business Plan | QA Manual | 40 | Week 2: 5; Week 3: 2023-02-10; Week 4: 20; Week 5: 14; Week 9: 2 | 1 |  | 1 |  | 0.25 |  |  | 4
| PWS Agreed | 0.5 | 8.25 | 6 | 2023-02-17 | 21 |  |  | 1 |  | 2 |  | 1 |  |  |  | 0.25 |  | 3 | 1
Financial Report I | Group Tender Presentations | 1 | Week 1: 5.25; Week 2: 7; Week 3: 2023-02-24; Week 4: 22 |  |  | 1 |  | 0.25 |  | 2 | 2
| Contracts | 2 | Week 1: 4.25; Week 2: 8; Week 3: 2023-03-03; Week 4: 23 |  |  |  |  | 0.25 |  | 3 | 1
| Financial Report II | 0.5 | Week 1: 6.25; Week 2: 9; Week 3: 2023-03-10; Week 4: 24 |  | 2 | 1 |  | 0.25 |  | 2 | 1
First Iteration | Final Test and Integration | 1 | Week 1: 6.25; Week 2: 10; Week 3: 2023-03-17; Week 4: 25 |  | 2 |  |  | 0.25 |  | 3 | 1
|  |  | Week 1: 5.25; Week 3: 2023-03-24; Week 4: 26; Week 6: 2 |  |  |  | 1 | 0.25 |  | 2
|  |  | Week 1: 4.75; Week 3: 2023-03-31; Week 4: 27 |  |  |  | 1 | 0.25 |  | 3 | 0.5
|  |  | Week 1: 3.25; Week 3: 2023-04-07; Week 4: 28 |  |  |  | 1 | 0.25 |  | 2
|  |  | Week 1: 5.25; Week 3: 2023-04-14; Week 4: 29 |  |  |  |  | 0.25 |  | 3 | 2
|  |  | Week 1: 7.75; Week 2: 1; Week 3: 2023-04-21; Week 4: 30; Week 10: 5 |  |  |  |  | 0.25 |  | 2 | 0.5
|  |  | Week 1: 11.25; Week 2: 2; Week 3: 2023-04-28; Week 4: 31; Week 10: 5 |  |  |  |  | 0.25 |  | 5 | 1
| Financial Report III | 0.5 | Week 1: 7.25; Week 2: 3; Week 3: 2023-05-05; Week 4: 32 |  |  | 1 |  | 0.25 |  | 5 | 1
| Financial Summary | 1 | Week 1: 9.25; Week 2: 4; Week 3: 2023-05-12; Week 4: 33 |  |  | 1 |  | 0.25 |  | 5 | 3
|  |  | Week 1: 8.25; Week 2: 5; Week 3: 2023-05-19; Week 4: 34; Week 6: 1 |  |  |  |  | 0.25 |  | 5 | 2
|  |  | Week 1: 7.25; Week 2: 6; Week 3: 2023-05-26; Week 4: 35; Week 6: 1 |  |  |  |  | 0.25 | 1 | 5
|  |  | Week 1: 8.25; Week 2: 7; Week 3: 2023-06-02; Week 4: 36 |  |  |  |  | 0.25 |  | 5 | 3
| All Deliverables |  | Week 1: 9.25; Week 2: 8; Week 3: 2023-06-09; Week 4: 37 |  |  |  |  | 0.25 |  | 5 | 4
|  |  | Week 1: 1.25; Week 2: 9; Week 3: 2023-06-16; Week 4: 38 |  |  |  |  | 0.25 |  |  | 1
|  |  | Week 1: 1.25; Week 2: 10; Week 3: 2023-06-23; Week 4: 39 |  |  |  |  | 0.25 |  |  | 1
60
Week Ending (Friday) | # | Projected hours | Week 2: Primary Tasks
2023-02-17 | 20 | 8.25 | Week 2: Design and General Doc Maintenance
2023-02-24 | 21 | 5.25 | Week 2: HTML Tour Planning
2023-03-03 | 22 | 4.25 | Week 2: HTML Tour Research
2023-03-10 | 23 | 6.25 | Week 2: Test and Integration Plans
2023-03-17 | 24 | 6.25 | Week 2: Test and Integration Plans
2023-03-24 | 25 | 5.25 | Week 2: QA Audits/ Code Comment Audits
2023-03-31 | 26 | 4.75 | Week 2: HTML Tour
2023-04-07 | 27 | 3.25 | Week 2: HTML Tour
2023-04-14 | 28 | 5.25 | Week 2: Admin for Term 2
2023-04-21 | 29 | 7.75 | Week 2: User Manual
2023-04-28 | 30 | 11.25 | Week 2: User Manual
2023-05-05 | 31 | 7.25 | Week 2: Financial Report Docs / HTML Tour
2023-05-12 | 32 | 9.25 | Week 2: Financial Report Docs/ HTML Tours
2023-05-19 | 33 | 8.25 | Week 2: HTML Tour
2023-05-26 | 34 | 7.25 | Week 2: HTML Tour
2023-06-02 | 35 | 8.25 | Week 2: All Documentation Prep
2023-06-09 | 36 | 9.25 | Week 2: All Documentation Delivered
2023-06-16 | 37 | 1.25 | Week 2: Document Maintenance
2023-06-23 | 38 | 1.25 | Week 2: Document Maintenance
Total
119.75