## Spending & Hours Summary
Employee | Individual Hours | Meeting Hours | Total Hours | Individual Labour Costs (£) | Meeting Labour Costs (£) | Total Labour Costs (£) | Actual | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39
Jonathan | 9 | 2.5 | 11.5 | 112.5 | 31.25 | 143.75 | Development - Client Software | 12.5 | 10.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Luke | 7 | 1.5 | 8.5 | 87.5 | 18.75 | 106.25 | Development - Server Software | 5.5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Will | 2.5 | 1 | 3.5 | 31.25 | 12.5 | 43.75 | Development Testing | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Srikanth | 7 | 1 | 8 | 87.5 | 12.5 | 100 | Integration and Testing | 4 | 6.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sophie | 9.5 | 1 | 10.5 | 118.75 | 12.5 | 131.25 | Documentation | 11.25 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Oliver | 8 | 0.5 | 8.5 | 100 | 6.25 | 106.25 | Marketing | 29.5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Matteo | 9.25 | 1.75 | 11 | 115.63 | 21.88 | 137.5 | Finance | 7.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Paul | 8 | 2 | 10 | 100 | 25 | 125 | Contracts | 3 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidharth | 9 | 2.25 | 11.25 | 112.5 | 28.13 | 140.63 | Expected
Sarujan | 11.5 | 0 | 11.5 | 143.75 | 0 | 143.75 | Development - Client Software | 4.5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fraser | 21.25 | 2.25 | 23.5 | 265.63 | 28.13 | 293.75 | Development - Server Software | 5.5 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 102 | 15.75 | 117.75 | 1275 | 196.88 | 1471.88 | Development Testing | 10 | 10.5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Integration and Testing | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Documentation | 8.25 | 5.25 | 4.25 | 6.25 | 6.25 | 5.25 | 4.75 | 3.25 | 5.25 | 7.75 | 11.25 | 7.25 | 9.25 | 8.25 | 7.25 | 8.25 | 9.25 | 0 | 0
[7 empty] | Marketing | 0 | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 10 | 0 | 0 | 0 | 0 | 0
[7 empty] | Finance | 3 | 5 | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 3 | 3 | 7 | 1 | 1 | 0 | 0
[7 empty] | Contracts | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
The subject matter for this financial report are weeks 21 & 22, which correspond to weeks 6 & 7 of the spring term. They are the weeks subsequent to the first submission of the Financial Business Plan, up to and including the week this report is due.
I have included indivual hours and the total incurred costs, not to convey personal contributions, but rather as proof of the structures we have in place for timekeeping purposes.
In our timesheets we also have a log which breaks down every task performed by each member and the hours spent, the area of development it concerns, and a description of the time they thought it would take and why they may have deviated from this estimate. I have omitted these from this report, instead providing a summary in the adjacent sheet.

## Variance Overview
Actual | Week 21 | Variance | Week 22 | Variance | Variance Analysis
Development - Client Software | 12.5 | 8 | 10.25 | 6.75 | we recently discovered a way to delegate resizing, as it pertains to components within windows, to one of the classes that is a foundation block upon which all other visual/media elements stem. As such, a lot of the scripts we had written that manually accounted for resizing had to be readjusted to be compatible with the new modus operandi. This also affected the associated test scripts, many of which specifically tested resizing capabilities.
Development - Server Software | 5.5 | 0 | 3 | -4 | Efforts had to be redirected towards the continuously evovling tender presentation, forcing us to push hours forward to the following weeks.
Development Testing | 2 | -8 | 2 | -8.5 | For the reasons explained in the "Development - Client Software" section, much effort was expended in adjusting pre-existing code, requiring little in terms of new testing strategies.
Integration and Testing | 4 | 4 | 6.25 | 6.25 | Due to uncertainty in the requirements of the Testing and Integration plan due in week 10, the integration team opted to bring forward the date for commencing work on this, to give us a better chance of meeting the requirements and quell some of our apprehensions.
Documentation | 11.25 | 3 | 6 | 0.75 | Writing the tender presentation unearthed some inconsistencies in our Functional Specification, which required some careful rewording. This was especially important as it is an adjunct to the Financial business plan.
Marketing | 29.5 | 29.5 | 12 | 12 | The scale of this oversight is due largely to the gross initial misunderstanding of what the tender presentation entailed, as well as underestimating its importance in both the project roadmap and the ongoing company appraisal. The perceived requirements changed dramatially several times, rendering large swathes of work unusable. The lack of any projected hours is due to our initial understanding of the presentation being an offloading of roadmaps, which we had already prepared and would therefore require no additional work. This is by far our biggest blunder, and we shall endeavour to keep it that way.
Finance | 7.5 | 4.5 | 2.5 | -2.5 | Preparing the Financial Business plan alerted us to the inefficiency of our previous timesheet format, which required a complete rework. Uncertainty over the requirements of this financial report caused me to overestimate the required time for preparing it.
Contracts | 3 | -1 | 0.5 | -3.5 | Errors in the development environments have forced us to defer some hours to next week.
Expected
Development - Client Software | 4.5 |  | 3.5
Development - Server Software | 5.5 |  | 7 |  |  | Projected Total Cost (only labour hrs): | 881.25 | 87.83% of the additional cost is due to the variance in the projected hours for marketing. I am therefore optimistic that the conclusions to be drawn from this report are not a prelude of a trend of gross overspending.
Development Testing | 10 |  | 10.5
Integration and Testing | 0 |  | 0 |  |  | Actual Total Cost(only labour hrs): | 1471.875
Documentation | 8.25 |  | 5.25
Marketing | 0 |  | 0 |  |  | Variance: | 590.625
Finance | 3 |  | 5
Contracts | 4 |  | 4