## Spending and Hours Summary
Employee | Individual Hours | Meeting Hours | Total Hours | Individual Labour Costs (£) | Meeting Labour Costs (£) | Total Labour Costs (£) | Actual | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39
Jonathan | 12 | 2.5 | 14.5 | 150 | 31.25 | 181.25 | Development - Client Software | 12.5 | 10.25 | 13.25 | 14.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Luke | 9.75 | 1.5 | 11.25 | 121.88 | 18.75 | 140.63 | Development - Server Software | 5.5 | 3 | 7.75 | 4.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Will | 12.5 | 3 | 15.5 | 156.25 | 37.5 | 193.75 | Development Testing | 2 | 2 | 1 | 1.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Srikanth | 7 | 1 | 8 | 87.5 | 12.5 | 100 | Integration and Testing | 4 | 6.25 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sophie | 17 | 5 | 22 | 212.5 | 62.5 | 275 | Documentation | 11.25 | 6 | 6.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Oliver | 15 | 0.5 | 15.5 | 187.5 | 6.25 | 193.75 | Marketing | 29.5 | 12 | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Matteo | 12.25 | 1.75 | 14 | 153.13 | 21.88 | 175 | Finance | 7.5 | 2.5 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Paul | 21.5 | 2 | 23.5 | 268.75 | 25 | 293.75 | Contracts | 3 | 0.5 | 9.25 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidharth | 21.5 | 3.25 | 24.75 | 268.75 | 40.63 | 309.38 | Expected
Sarujan | 15 | 0 | 15 | 187.5 | 0 | 187.5 | Development - Client Software | 4.5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fraser | 31.75 | 3.5 | 35.25 | 396.88 | 43.75 | 440.63 | Development - Server Software | 5.5 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 175.25 | 24 | 199.25 | 2190.63 | 300 | 2490.63 | Development Testing | 10 | 10.5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Integration and Testing | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Documentation | 8.25 | 5.25 | 4.25 | 6.25 | 6.25 | 5.25 | 4.75 | 3.25 | 5.25 | 7.75 | 11.25 | 7.25 | 9.25 | 8.25 | 7.25 | 8.25 | 9.25 | 0 | 0
[7 empty] | Marketing | 0 | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 10 | 0 | 0 | 0 | 0 | 0
[7 empty] | Finance | 3 | 5 | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 3 | 3 | 7 | 1 | 1 | 0 | 0
[7 empty] | Contracts | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
This report concerns primarily weeks 23 & 24 - weeks 8 & 9 of the spring term - although the total labour costs and hours displayed in the Spending and Hours Summary are counted from Financial Business Plan submission in week 20.
In our timesheets we also have a log which breaks down every task performed by each member and the hours spent, the area of development it concerns, and a description of the time they thought it would take and why they may have deviated from this estimate. I have omitted these from this report, instead providing a summary in the Variance Overview sheet.

## Variance Overview
Actual | Week 21 | Variance | Week 22 | Variance | Week 23 | Variance | Week 24 | Variance | Variance Analysis
Development - Client Software | 12.5 | 8 | 10.25 | 6.75 | 13.25 | 13.25 | 10.75 | 10.75 | We had expected to have finished writing the code for both our client app and server app by week 23 (week 8 spring term), but this has obviosuly not panned out as expected. We planned for this and have ample time before we intend to commence the integration phase of the development plan. Development hasn't hit any walls and the variance is due solely to discrepancies in coding abilities between group members and frugal estimates on our part of how much time some aspects of the code would require.
Development - Server Software | 5.5 | 0 | 3 | -4 | 7.75 | 3.75 | 4.75 | 4.75 | The negative variance from week 22 has been transferred to weeks 23 & 24. Some unfamiliarity with a few of the testing libraries meant some work took longer than predicted.
Development Testing | 2 | -8 | 2 | -8.5 | 1 | -3 | 5.75 | 5.75 | Some classes in both server and client side cannot have their functionality exaustively tested as they require other classes to be complete and in some cases for entire packages to be finished and working. In light of this, the split between code containing tests and the code it is testing has not been as equal as we initially anticipated, especially for visual elements. The work has leant more heavily towards functional code development over testing code development.
Integration and Testing | 4 | 4 | 6.25 | 6.25 | 10 | 10 | 0 | -9 | Planning for the Integration and Testing plan began early as is clear in the tables. The 18 scheduled hours for weeks 24 & 25 have been brought forward as is evident from the large negative variance in week 24. This decision was made due to the difficulties and therefore ensuing anxiety that comes from preparing a plan such as we have never done before.
Documentation | 11.25 | 3 | 6 | 0.75 | 6.5 | 2.25 | 1.5 | -4.75 | Hours not equally distributed between the two weeks but the total hours are close to predicted and overall a negative variance.
Marketing | 29.5 | 29.5 | 12 | 12 | 0.5 | -5.5 | 1 | -5 | Some members of the team are preoccupied with software development, and we are waiting for approval from the ethics board for our online surveys.
Finance | 7.5 | 4.5 | 2.5 | -2.5 | 0 | -3 | 3 | -2 | As financial manager I had allocated a couple of hours per week for maintaining and updating the timesheets as per our needs, but so far the current structure works well and hasn't required any further input.
Contracts | 3 | -1 | 0.5 | -3.5 | 9.25 | 9.25 | 4.5 | 4.5 | Bulk of the work was deferred as already explained in the first financial report. Implementing TDD in an unfamiliar programming language and IDE proved harder than expected.
Expected
Development - Client Software | 4.5 |  | 3.5 |  | 0 |  | 0 |  |  |  | Weeks 23 & 24 |  |  | Total
Development - Server Software | 5.5 |  | 7 |  | 4 |  | 0
Development Testing | 10 |  | 10.5 |  | 4 |  | 0 |  |  | Projected Total Cost (only labour hrs): |  | 593.75 | Projected Total Cost (only labour hrs): |  | 1475
Integration and Testing | 0 |  | 0 |  | 0 |  | 9
Documentation | 8.25 |  | 5.25 |  | 4.25 |  | 6.25 |  |  | Actual Total Cost(only labour hrs): |  | 993.75 | Actual Total Cost(only labour hrs): |  | 2465.625
Marketing | 0 |  | 0 |  | 6 |  | 6
Finance | 3 |  | 5 |  | 3 |  | 5 |  |  | Variance: |  | 400 | Variance: |  | 990.625
Contracts | 4 |  | 4 |  | 0 |  | 0
There are 54.75 projected hours left until the next loan payment arrives. Looking at the current spending trend since week 20, we have underestimated our labour costs by about 60%. The extra cost incurred if this trend continues equates to around £410, which added to current variance gives £1400 overspend when the second loan payment arrives in week 30. We had calculated in the FInancial Business Plan that we would have £2614 surplus at the end of week 29, so with our current overspending trend we are not at risk of bankrupcy.