## Spending and Hours Summary
Employee | Individual Hours | Meeting Hours | Total Hours | Individual Labour Costs (£) | Meeting Labour Costs (£) | Total Labour Costs (£) | Actual | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39
Jonathan | 34 | 4.5 | 38.5 | 425 | 56.25 | 481.25 | Development - Client Software | 12.5 | 10.25 | 13.25 | 12.75 | 15.75 | 14 | 0 | 0 | 13 | 5.25 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Luke | 10.5 | 1.5 | 12 | 131.25 | 18.75 | 150 | Development - Server Software | 5.5 | 3 | 7.75 | 4.75 | 6.5 | 0 | 0 | 0 | 8.5 | 3.25 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Will | 17 | 7 | 24 | 212.5 | 87.5 | 300 | Development Testing | 2 | 2 | 1 | 5.75 | 2.5 | 0 | 0 | 0 | 4.5 | 4 | 8 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Srikanth | 29 | 1 | 30 | 362.5 | 12.5 | 375 | Integration and Testing | 4 | 6.25 | 10 | 1 | 5.5 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sophie | 49.5 | 6.5 | 56 | 618.75 | 81.25 | 700 | Documentation | 11.25 | 6 | 6.5 | 2.5 | 14 | 0 | 0 | 0 | 0 | 11.5 | 14.75 | 6.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Oliver | 21 | 2.5 | 23.5 | 262.5 | 31.25 | 293.75 | Marketing | 29.5 | 12 | 0.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | 3.5 | 11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Matteo | 18.5 | 3.5 | 22 | 231.25 | 43.75 | 275 | Finance | 7.5 | 2.5 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0.25 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Paul | 47.5 | 5.25 | 52.75 | 593.75 | 65.63 | 659.38 | Contracts | 3 | 0.5 | 9.25 | 6.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidharth | 49 | 8.25 | 57.25 | 612.5 | 103.13 | 715.63 | Expected
Sarujan | 15 | 0 | 15 | 187.5 | 0 | 187.5 | Development - Client Software | 4.5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fraser | 37.5 | 4.75 | 42.25 | 468.75 | 59.38 | 528.13 | Development - Server Software | 5.5 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 328.5 | 44.75 | 373.25 | 4106.25 | 559.38 | 4665.63 | Development Testing | 10 | 10.5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Integration and Testing | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Documentation | 8.25 | 5.25 | 4.25 | 6.25 | 6.25 | 5.25 | 4.75 | 3.25 | 5.25 | 7.75 | 11.25 | 7.25 | 9.25 | 8.25 | 7.25 | 8.25 | 9.25 | 0 | 0
[7 empty] | Marketing | 0 | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 10 | 0 | 0 | 0 | 0 | 0
[7 empty] | Finance | 3 | 5 | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 3 | 3 | 7 | 1 | 1 | 0 | 0
[7 empty] | Contracts | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
This report concerns primarily weeks 25 -32, although the total labour costs and hours displayed in the Spending and Hours Summary are counted from Financial Business Plan submission in week 20.
In our timesheets we also have a log which breaks down every task performed by each member and the hours spent, the area of development it concerns, and a description of the time they thought it would take and why they may have deviated from this estimate. I have omitted these from this report, instead providing a summary in the Variance Overview sheet.

## Variance Overview
Actual | Week 21 | Variance | Week 22 | Variance | Week 23 | Variance | Week 24 | Variance | Week 25 | Variance | Week 26 | Variance | Week 27 | Variance | Week 28 | Variance | Week 29 | Variance | Week 30 | Variance | Week 31 | Variance | Week 32 | Variance | Variance Analysis
Development - Client Software | 12.5 | 8 | 10.25 | 6.75 | 13.25 | 13.25 | 10.75 | 10.75 | 15.75 | 15.75 | 14 | 14 | 0 | 0 | 0 | 0 | 13 | 13 | 5.25 | 5.25 | 5 | 5 | 2 | 2 | We had expected to have finished client-side development at the end of last term, but this has obviously not transpired. Failure to properly assess the discrepancies in programming proficiency amongst group members has led to gross underestimation of required development hours. This has led to the more experienced programmers having to plug the gaps and rewrite inefficient or erroneous code.
Development - Server Software | 5.5 | 0 | 3 | -4 | 7.75 | 3.75 | 4.75 | 4.75 | 6.5 | 6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5 | 8.5 | 3.25 | 3.25 | 2 | 2 | 1 | 1 | We had expected to have finished server-side development at the end of last term, but the finishing touches have bled into the start of this term; development is now finished. This was due to some extra research needed for some aspects of the code which weren't working as expected.
Development Testing | 2 | -8 | 2 | -8.5 | 1 | -3 | 5.75 | 5.75 | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 4.5 | 4 | 4 | 8 | 8 | 0.5 | 0.5 | Difficulties in adhering to strict test-driven development procedures, especially for visual elements, has forced us to perform more testing than originally anticipated, requiring more effort to be exaustive as a result of writing tests post development.
Integration and Testing | 4 | 4 | 6.25 | 6.25 | 10 | 10 | 0 | -9 | 5.5 | -3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 1.5 | 1.5 | 0 | 0 | Net overestimation of worked hours due to being behind schedule with code development. For obvious reasons, integration efforts cannot begin in earnest until the code is complete, so I expect these predicted hours to be worked in the coming weeks.
Documentation | 11.25 | 3 | 6 | 0.75 | 6.5 | 2.25 | 1.5 | -4.75 | 14 | 7.75 | 0 | -5.25 | 0 | -4.75 | 0 | -3.25 | 0 | -5.25 | 11.5 | 3.75 | 14.75 | 3.5 | 6.25 | -1 | Total predicted hours for this period is quite accurate, the exact timeframe has not been strictly followed. This is due to the decision to not work during the spring break, based on our appraisal of our progress at the end of last term.
Marketing | 29.5 | 29.5 | 12 | 12 | 0.5 | -5.5 | 1 | -5 | 0.5 | -5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5 | 3.5 | 11.5 | 11.5 | 0 | -4 | Total predicted hours for this period is quite accurate, the exact timeframe has not been strictly followed. This is due to the decision to not work during the spring break, based on our appraisal of our progress at the end of last term. However, I predict that in the period to follow the hours will be significantly greater than expected, due to only recent understanding of how prominent a role future marketing is going to play in our final finance report due on the 26th of May.
Finance | 7.5 | 4.5 | 2.5 | -2.5 | 0 | -3 | 3 | -2 | 0 | -3 | 0 | -3 | 0 | -3 | 0 | -3 | 0 | -3 | 0.25 | -2.75 | 1 | -2 | 4 | -1 | As manager I am very happy with the level of functionality we were able to give to our timesheets last term, meaning that we have had no need to maintain or develop it further, as it fully meets our requirements and provides total transparency and accountability. I therefore overestimated how many hours would be worked by the finance team during this period.
Contracts | 3 | -1 | 0.5 | -3.5 | 9.25 | 9.25 | 4.5 | 4.5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Concluded last term.
Expected
Development - Client Software | 4.5 |  | 3.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Development - Server Software | 5.5 |  | 7 |  | 4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Development Testing | 10 |  | 10.5 |  | 4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Integration and Testing | 0 |  | 0 |  | 0 |  | 9 |  | 9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 12 |  | 0 |  | 0
Documentation | 8.25 |  | 5.25 |  | 4.25 |  | 6.25 |  | 6.25 |  | 5.25 |  | 4.75 |  | 3.25 |  | 5.25 |  | 7.75 |  | 11.25 |  | 7.25
Marketing | 0 |  | 0 |  | 6 |  | 6 |  | 6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 4
Finance | 3 |  | 5 |  | 3 |  | 5 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 5
Contracts | 4 |  | 4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[5 empty] | Weeks 25-30 | [6 empty] | Weeks 25-32 | [6 empty] | Total
|  |  | Projected Total Cost (only labour hrs): |  |  | 968.75 |  |  |  | Projected Total Cost (only labour hrs): |  |  | 1350 |  |  |  | Projected Total Cost (only labour hrs): |  |  | 2825
|  |  | Actual Total Cost(only labour hrs): |  |  | 1418.75 |  |  |  | Actual Total Cost(only labour hrs): |  |  | 2137.5 |  |  |  | Actual Total Cost(only labour hrs): |  |  | 4603.125
|  |  | Variance: |  |  | 450 |  |  |  | Variance: |  |  | 787.5 |  |  |  | Variance: |  |  | 1778.125
|  |  | Our overspend for weeks 25-30 was almost exactly as predicted in the previous financial report. As expected, we maintained the trend of 60% overspend and did not go bankrupt. | [6 empty] | Variance mostly due to unexpected continuation of software development. Balanced by overestimate in Finance Department spending and by delay of integration efforts. | [6 empty] | Our overspending trend has remained the same, at roughly 62%. If we maintain this level of spending we will go bankrupt by the end of week 35. Underestimates of development and marketing hours are the main drivers of our predicament. We are currently discussing measures to mitigate this, without compromising the quality of our product. A detailed plan will be laid out in the Final Finance Report due on the 26th of May.